## Dashboard
Q3 Weekly Checklist & Industrial Content Plan
Q3 focus: produce consistent industrial tutorials/articles, integrate Solehin video content, and coordinate targeted tutorials with Iffah for ActiveCampaign.
Weekly Content Target |  | Q3 Content Target |  | Video-supported Target |  | ActiveCampaign Target
2–3 per week |  | 24–36 pieces |  | 24–36 pieces |  | 8–12 tutorials
Live Progress Summary
Published / Completed | Video Included | AC Submitted | Checklist Done | Blocked Items | Views/Clicks Added
2 | 2 | 0 | 0 | 0 | 0
Month | Content Target | Published / Completed | Video Included | ActiveCampaign Submitted
July 2026 | 8–12 | 2 | 2 | 0
August 2026 | 8–12 | 0 | 0 | 0
September 2026 | 8–12 | 0 | 0 | 0
Weekly Operating Rhythm
Monday | Check on Solehin Tiktok Video list from Google Drive. Draft 1st article.
Tuesday | Upload 1st youtube video. Publish 1st article.
Wednesday | Check on Solehin Tiktok Video list from Google Drive. Draft 2nd article.
Thursday | Upload 2nd youtube video. Publish 2nd article
Friday | If 1st week, draft 3rd article. If 2nd week, publish 3rd article. Update tracker. Identify article for ActiveCampaign with Iffah.
Monthly | Review total published content on Youtube, Industrial articles, ActiveCampaign list, and top-performing content.
Q3 End | Summarize published pieces, video integrations, ActiveCampaign results, and lessons for appraisal.

## Content Tracker
Week | Date Range | Content Title | Product / Category | Content Type | Status | Priority | Owner / PIC | Draft Start Date | Publish Date | Tutorial / Article URL | Solehin Video Included | YouTube Link | ActiveCampaign Submitted | AC Status | Baseline Views / Clicks | Latest Views / Clicks | Views / Clicks Added | Notes
W01 | 05 Jul – 11 Jul 2026 | What is SCADA? A Simple Introduction to Industrial Monitoring | IRIV Pi Control | Article | Published | High | Me | 2026-07-06 | 2026-07-07 | https://my.cytron.io/tutorial/what-is-scada-a-simple-introduction-to-industrial-monitoring | Yes | https://www.youtube.com/shorts/WfHgmy9Kvp8 | Pending | Not Submitted
W01 | 05 Jul – 11 Jul 2026 | How AI Detects Defects in Product Quality Inspection | IRIV EdgeAI CM5 | Article | Published | High | Me | 2026-07-09 | 2026-07-09 | https://my.cytron.io/tutorial/how-ai-detects-defects-in-product-quality-inspection | Yes | https://www.youtube.com/shorts/xQniEPTFj9U | Pending | Not Submitted
W02 | 12 Jul – 18 Jul 2026 | Industry Dashboard with IRIV | IRIV Pi Control | Article | Planning | High | Me | 2026-07-10 |  |  | Pending |  | Pending | Not Submitted
W02 | 12 Jul – 18 Jul 2026 | Can IRIV Smarthub CM5 Create MES System | IRIV SmartHub CM5 | Article
W02 | 12 Jul – 18 Jul 2026 | IRIV Pi Control with SCADA | IRIV Pi Control | Article
W03 | 19 Jul – 25 Jul 2026 | AI PPE Zone Monitoring | IRIV EdgeAI CM5 | Article
W03 | 19 Jul – 25 Jul 2026 | Best AI Tools for Industry | Industrial | Article
W04 | 26 Jul – 01 Aug 2026 | 84 Days Stress Test for IRIV Smarthub CM5 | IRIV SmartHub CM5 | Article
W04 | 26 Jul – 01 Aug 2026 | IRIV Pi Control Use Cases (Weather Station) | IRIV Pi Control | Article
W04 | 26 Jul – 01 Aug 2026 | IRIV EdgeAI CM5 Use Cases (Packaging Detection) | IRIV EdgeAI CM5 | Article
W05 | 02 Aug – 08 Aug 2026 | IRIV EdgeAI CM5 Use Cases (Sample Application) | IRIV EdgeAI CM5 | Article
W05 | 02 Aug – 08 Aug 2026 | IRIV Pi Control Use Cases (Energy Monitoring) | IRIV Pi Control | Article
W06 | 09 Aug – 15 Aug 2026 | IRIV EdgeAI CM5 Use Cases (PPE Safety Detection) | IRIV EdgeAI CM5 | Article
W06 | 09 Aug – 15 Aug 2026 | IRIV Pi Control Use Cases (System Failure Notification) | IRIV Pi Control | Article
W06 | 09 Aug – 15 Aug 2026 | IRIV SmartHub CM5 Use Cases (Digital Signage) | IRIV SmartHub CM5 | Article
W07 | 16 Aug – 22 Aug 2026
W07 | 16 Aug – 22 Aug 2026
W08 | 23 Aug – 29 Aug 2026
W08 | 23 Aug – 29 Aug 2026
W08 | 23 Aug – 29 Aug 2026
W09 | 30 Aug – 05 Sep 2026
W09 | 30 Aug – 05 Sep 2026
W10 | 06 Sep – 12 Sep 2026
W10 | 06 Sep – 12 Sep 2026
W10 | 06 Sep – 12 Sep 2026
W11 | 13 Sep – 19 Sep 2026
W11 | 13 Sep – 19 Sep 2026
W12 | 20 Sep – 26 Sep 2026
W12 | 20 Sep – 26 Sep 2026
W12 | 20 Sep – 26 Sep 2026
W13 | 27 Sep – 03 Oct 2026
W13 | 27 Sep – 03 Oct 2026

## Weekly Checklist
Week | Date Range | Area | Checklist Item | Status | Owner / PIC | Notes
W01 | 05 Jul – 11 Jul 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: What is SCADA? A Simple Introduction to Industrial Monitoring; How AI Detects Defects in Product Quality Inspection
W01 | 05 Jul – 11 Jul 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W01 | 05 Jul – 11 Jul 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W01 | 05 Jul – 11 Jul 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W01 | 05 Jul – 11 Jul 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W01 | 05 Jul – 11 Jul 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W01 | 05 Jul – 11 Jul 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W01 | 05 Jul – 11 Jul 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W01 | 05 Jul – 11 Jul 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W01 | 05 Jul – 11 Jul 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W01 | 05 Jul – 11 Jul 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W01 | 05 Jul – 11 Jul 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W01 | 05 Jul – 11 Jul 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W01 | 05 Jul – 11 Jul 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W01 | 05 Jul – 11 Jul 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W01 | 05 Jul – 11 Jul 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W02 | 12 Jul – 18 Jul 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: Industry Dashboard with IRIV; Can IRIV Smarthub CM5 Create MES System; IRIV Pi Control with SCADA
W02 | 12 Jul – 18 Jul 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W02 | 12 Jul – 18 Jul 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W02 | 12 Jul – 18 Jul 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W02 | 12 Jul – 18 Jul 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W02 | 12 Jul – 18 Jul 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W02 | 12 Jul – 18 Jul 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W02 | 12 Jul – 18 Jul 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W02 | 12 Jul – 18 Jul 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W02 | 12 Jul – 18 Jul 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W02 | 12 Jul – 18 Jul 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W02 | 12 Jul – 18 Jul 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W02 | 12 Jul – 18 Jul 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W02 | 12 Jul – 18 Jul 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W02 | 12 Jul – 18 Jul 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W02 | 12 Jul – 18 Jul 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W03 | 19 Jul – 25 Jul 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: AI PPE Zone Monitoring; Best AI Tools for Industry
W03 | 19 Jul – 25 Jul 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W03 | 19 Jul – 25 Jul 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W03 | 19 Jul – 25 Jul 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W03 | 19 Jul – 25 Jul 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W03 | 19 Jul – 25 Jul 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W03 | 19 Jul – 25 Jul 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W03 | 19 Jul – 25 Jul 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W03 | 19 Jul – 25 Jul 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W03 | 19 Jul – 25 Jul 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W03 | 19 Jul – 25 Jul 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W03 | 19 Jul – 25 Jul 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W03 | 19 Jul – 25 Jul 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W03 | 19 Jul – 25 Jul 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W03 | 19 Jul – 25 Jul 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W03 | 19 Jul – 25 Jul 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W04 | 26 Jul – 01 Aug 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: 84 Days Stress Test for IRIV Smarthub CM5; IRIV Pi Control Use Cases (Weather Station); IRIV EdgeAI CM5 Use Cases (Packaging Detection)
W04 | 26 Jul – 01 Aug 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W04 | 26 Jul – 01 Aug 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W04 | 26 Jul – 01 Aug 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W04 | 26 Jul – 01 Aug 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W04 | 26 Jul – 01 Aug 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W04 | 26 Jul – 01 Aug 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W04 | 26 Jul – 01 Aug 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W04 | 26 Jul – 01 Aug 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W04 | 26 Jul – 01 Aug 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W04 | 26 Jul – 01 Aug 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W04 | 26 Jul – 01 Aug 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W04 | 26 Jul – 01 Aug 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W04 | 26 Jul – 01 Aug 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W04 | 26 Jul – 01 Aug 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W04 | 26 Jul – 01 Aug 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W05 | 02 Aug – 08 Aug 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: IRIV EdgeAI CM5 Use Cases (Sample Application); IRIV Pi Control Use Cases (Energy Monitoring)
W05 | 02 Aug – 08 Aug 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W05 | 02 Aug – 08 Aug 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W05 | 02 Aug – 08 Aug 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W05 | 02 Aug – 08 Aug 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W05 | 02 Aug – 08 Aug 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W05 | 02 Aug – 08 Aug 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W05 | 02 Aug – 08 Aug 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W05 | 02 Aug – 08 Aug 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W05 | 02 Aug – 08 Aug 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W05 | 02 Aug – 08 Aug 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W05 | 02 Aug – 08 Aug 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W05 | 02 Aug – 08 Aug 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W05 | 02 Aug – 08 Aug 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W05 | 02 Aug – 08 Aug 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W05 | 02 Aug – 08 Aug 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W06 | 09 Aug – 15 Aug 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | Planned content: IRIV EdgeAI CM5 Use Cases (PPE Safety Detection); IRIV Pi Control Use Cases (System Failure Notification); IRIV SmartHub CM5 Use Cases (Digital Signage)
W06 | 09 Aug – 15 Aug 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W06 | 09 Aug – 15 Aug 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W06 | 09 Aug – 15 Aug 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W06 | 09 Aug – 15 Aug 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W06 | 09 Aug – 15 Aug 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W06 | 09 Aug – 15 Aug 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W06 | 09 Aug – 15 Aug 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W06 | 09 Aug – 15 Aug 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W06 | 09 Aug – 15 Aug 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W06 | 09 Aug – 15 Aug 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W06 | 09 Aug – 15 Aug 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W06 | 09 Aug – 15 Aug 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W06 | 09 Aug – 15 Aug 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W06 | 09 Aug – 15 Aug 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W06 | 09 Aug – 15 Aug 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W07 | 16 Aug – 22 Aug 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W07 | 16 Aug – 22 Aug 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W07 | 16 Aug – 22 Aug 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W07 | 16 Aug – 22 Aug 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W07 | 16 Aug – 22 Aug 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W07 | 16 Aug – 22 Aug 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W07 | 16 Aug – 22 Aug 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W07 | 16 Aug – 22 Aug 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W07 | 16 Aug – 22 Aug 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W07 | 16 Aug – 22 Aug 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W07 | 16 Aug – 22 Aug 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W07 | 16 Aug – 22 Aug 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W07 | 16 Aug – 22 Aug 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W07 | 16 Aug – 22 Aug 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W07 | 16 Aug – 22 Aug 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W07 | 16 Aug – 22 Aug 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W08 | 23 Aug – 29 Aug 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W08 | 23 Aug – 29 Aug 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W08 | 23 Aug – 29 Aug 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W08 | 23 Aug – 29 Aug 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W08 | 23 Aug – 29 Aug 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W08 | 23 Aug – 29 Aug 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W08 | 23 Aug – 29 Aug 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W08 | 23 Aug – 29 Aug 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W08 | 23 Aug – 29 Aug 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W08 | 23 Aug – 29 Aug 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W08 | 23 Aug – 29 Aug 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W08 | 23 Aug – 29 Aug 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W08 | 23 Aug – 29 Aug 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W08 | 23 Aug – 29 Aug 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W08 | 23 Aug – 29 Aug 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W08 | 23 Aug – 29 Aug 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W09 | 30 Aug – 05 Sep 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W09 | 30 Aug – 05 Sep 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W09 | 30 Aug – 05 Sep 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W09 | 30 Aug – 05 Sep 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W09 | 30 Aug – 05 Sep 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W09 | 30 Aug – 05 Sep 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W09 | 30 Aug – 05 Sep 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W09 | 30 Aug – 05 Sep 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W09 | 30 Aug – 05 Sep 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W09 | 30 Aug – 05 Sep 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W09 | 30 Aug – 05 Sep 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W09 | 30 Aug – 05 Sep 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W09 | 30 Aug – 05 Sep 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W09 | 30 Aug – 05 Sep 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W09 | 30 Aug – 05 Sep 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W09 | 30 Aug – 05 Sep 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W10 | 06 Sep – 12 Sep 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W10 | 06 Sep – 12 Sep 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W10 | 06 Sep – 12 Sep 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W10 | 06 Sep – 12 Sep 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W10 | 06 Sep – 12 Sep 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W10 | 06 Sep – 12 Sep 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W10 | 06 Sep – 12 Sep 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W10 | 06 Sep – 12 Sep 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W10 | 06 Sep – 12 Sep 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W10 | 06 Sep – 12 Sep 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W10 | 06 Sep – 12 Sep 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W10 | 06 Sep – 12 Sep 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W10 | 06 Sep – 12 Sep 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W10 | 06 Sep – 12 Sep 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W10 | 06 Sep – 12 Sep 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W10 | 06 Sep – 12 Sep 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W11 | 13 Sep – 19 Sep 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W11 | 13 Sep – 19 Sep 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W11 | 13 Sep – 19 Sep 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W11 | 13 Sep – 19 Sep 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W11 | 13 Sep – 19 Sep 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W11 | 13 Sep – 19 Sep 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W11 | 13 Sep – 19 Sep 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W11 | 13 Sep – 19 Sep 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W11 | 13 Sep – 19 Sep 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W11 | 13 Sep – 19 Sep 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W11 | 13 Sep – 19 Sep 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W11 | 13 Sep – 19 Sep 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W11 | 13 Sep – 19 Sep 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W11 | 13 Sep – 19 Sep 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W11 | 13 Sep – 19 Sep 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W11 | 13 Sep – 19 Sep 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W12 | 20 Sep – 26 Sep 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W12 | 20 Sep – 26 Sep 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W12 | 20 Sep – 26 Sep 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W12 | 20 Sep – 26 Sep 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W12 | 20 Sep – 26 Sep 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W12 | 20 Sep – 26 Sep 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W12 | 20 Sep – 26 Sep 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W12 | 20 Sep – 26 Sep 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W12 | 20 Sep – 26 Sep 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W12 | 20 Sep – 26 Sep 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W12 | 20 Sep – 26 Sep 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W12 | 20 Sep – 26 Sep 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W12 | 20 Sep – 26 Sep 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W12 | 20 Sep – 26 Sep 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W12 | 20 Sep – 26 Sep 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W12 | 20 Sep – 26 Sep 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks
W13 | 27 Sep – 03 Oct 2026 | Planning | Review planned content titles from Content Tracker | Not Started | Me | No title planned yet in Content Tracker
W13 | 27 Sep – 03 Oct 2026 | Planning | Confirm 2–3 industrial tutorial/article topics for the week | Not Started | Me | Target: minimum 2, ideal 3 pieces
W13 | 27 Sep – 03 Oct 2026 | Video Integration | Check Solehin TikTok video list from Google Drive | Not Started | Me | Match suitable videos with planned articles
W13 | 27 Sep – 03 Oct 2026 | Drafting | Draft 1st article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W13 | 27 Sep – 03 Oct 2026 | YouTube | Upload or prepare 1st YouTube video | Not Started | Me | Use related Solehin video if available
W13 | 27 Sep – 03 Oct 2026 | Publishing | Publish or prepare 1st article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W13 | 27 Sep – 03 Oct 2026 | Video Integration | Check/confirm 2nd suitable Solehin video | Not Started | Me | Use if the week has a matching video
W13 | 27 Sep – 03 Oct 2026 | Drafting | Draft 2nd article/tutorial | Not Started | Me | Focus on industrial tutorial/article pipeline
W13 | 27 Sep – 03 Oct 2026 | YouTube | Upload or prepare 2nd YouTube video | Not Started | Me | Use related Solehin video if available
W13 | 27 Sep – 03 Oct 2026 | Publishing | Publish or prepare 2nd article/tutorial | Not Started | Me | Update URL in Content Tracker after publish
W13 | 27 Sep – 03 Oct 2026 | Optional Content | Draft or publish 3rd article/tutorial if available | Not Started | Me | Use alternating cadence if needed: draft in week 1, publish in week 2
W13 | 27 Sep – 03 Oct 2026 | ActiveCampaign | Identify targeted article/tutorial for ActiveCampaign with Iffah | Not Started | Me | Prioritize content with clear product CTA
W13 | 27 Sep – 03 Oct 2026 | ActiveCampaign | Prepare title, short summary, CTA, and product links | Not Started | Me | Add details into ActiveCampaign Queue
W13 | 27 Sep – 03 Oct 2026 | ActiveCampaign | Confirm ActiveCampaign inclusion status with Iffah | Not Started | Iffah | Update AC Status in Content Tracker
W13 | 27 Sep – 03 Oct 2026 | Tracking | Update Content Tracker with URL, YouTube link, AC status, and views/clicks | Not Started | Me | Record baseline where available
W13 | 27 Sep – 03 Oct 2026 | Weekly Review | Review completed content, delayed items, blockers, and next week follow-up | Not Started | Me | Use notes for blockers and carry-forward tasks

## ActiveCampaign Queue
Week | Tutorial / Article Title | Product / Category | Target Audience | CTA / Product Link | Submitted to Iffah | AC Status | Submitted Date | Notes
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted
[5 empty] | Pending | Not Submitted

## Lists
Week | Date Range | Start Date | End Date | Content Status | Checklist Status | Content Type | Yes/No/Pending | AC Status | Priority | PIC
W01 | 05 Jul – 11 Jul 2026 | 2026-07-05 | 2026-07-11 | Not Started | Not Started | Tutorial | Yes | Not Submitted | High | Me
W02 | 12 Jul – 18 Jul 2026 | 2026-07-12 | 2026-07-18 | Planning | In Progress | Article | No | Submitted to Iffah | Medium | Iffah
W03 | 19 Jul – 25 Jul 2026 | 2026-07-19 | 2026-07-25 | Drafting | Done | Video-supported Article | Pending | Added to ActiveCampaign | Low | Solehin
W04 | 26 Jul – 01 Aug 2026 | 2026-07-26 | 2026-08-01 | Technical Review | Blocked | Product Use Case |  | Scheduled |  | IT
W05 | 02 Aug – 08 Aug 2026 | 2026-08-02 | 2026-08-08 | Ready to Publish |  | Technical Guide |  | Sent |  | Education Team
W06 | 09 Aug – 15 Aug 2026 | 2026-08-09 | 2026-08-15 | Published |  | Launch Support Content |  | Needs Follow-up |  | Industry Team
W07 | 16 Aug – 22 Aug 2026 | 2026-08-16 | 2026-08-22 | Completed |  |  |  | Not Suitable |  | International Team
W08 | 23 Aug – 29 Aug 2026 | 2026-08-23 | 2026-08-29 | Delayed | [5 empty] | Marketing Team
W09 | 30 Aug – 05 Sep 2026 | 2026-08-30 | 2026-09-05 | Blocked
W10 | 06 Sep – 12 Sep 2026 | 2026-09-06 | 2026-09-12
W11 | 13 Sep – 19 Sep 2026 | 2026-09-13 | 2026-09-19
W12 | 20 Sep – 26 Sep 2026 | 2026-09-20 | 2026-09-26
W13 | 27 Sep – 03 Oct 2026 | 2026-09-27 | 2026-10-03